## 3-Point Estimates
Phase | Feature / Module | Optimistic (O) hrs | Most Likely (M) hrs | Pessimistic (P) hrs | PERT Expected hrs | Std Deviation (±) | Optimistic Cost ($) | Most Likely Cost ($) | Pessimistic Cost ($) | PERT Expected Cost ($) | Team | Risk / Comments
Phase 1: Core MVP | Foundation - Requirements Analysis & Technical Discovery | 30 | 40 | 60 | 42 | 5 | 1950 | 2600 | 3900 | 2730 | PM, SA | Scope clarity risk: RFP has ambiguous areas
Phase 1: Core MVP | Foundation - Architecture & Database Schema Design | 25 | 30 | 45 | 32 | 3.3 | 1625 | 1950 | 2925 | 2080 | SA | Schema complexity may increase with gamification data
Phase 1: Core MVP | Foundation - Azure Cloud Environment Setup & CI/CD Pipelines | 50 | 70 | 100 | 72 | 8.3 | 3250 | 4550 | 6500 | 4680 | DevOps | Azure subscription + permissions can cause delays
Phase 1: Core MVP | Foundation - Local Developer Testing Setup (Docker Compose) | 30 | 40 | 55 | 41 | 4.2 | 1950 | 2600 | 3575 | 2665 | DevOps, BE | Service interdependencies can complicate local setup
Phase 1: Core MVP | Layer 1: Edge & UI - UX Conceptualization, Visual Identity | 100 | 130 | 180 | 133 | 13.3 | 6500 | 8450 | 11700 | 8645 | Designer, FE | Stakeholder feedback loops can stretch design cycles
Phase 1: Core MVP | Layer 1: Edge & UI - Student Tablet Mobile Application (PWA) | 200 | 260 | 360 | 267 | 26.7 | 13000 | 16900 | 23400 | 17355 | FE | POS, QR, offline caching add mobile complexity
Phase 1: Core MVP | Layer 1: Edge & UI - Teacher & Volunteer Monitoring Dashboard | 60 | 80 | 110 | 82 | 8.3 | 3900 | 5200 | 7150 | 5330 | FE | Real-time data binding and WebSocket integration risk
Phase 1: Core MVP | Layer 1: Edge & UI - Admin Core: User Mgmt, Roles, Moderation | 90 | 120 | 170 | 123 | 13.3 | 5850 | 7800 | 11050 | 7995 | FE, BE | Complex RBAC flows often have edge case bugs
Phase 1: Core MVP | Layer 1: Edge & UI - Admin Automation: Event Controllers | 45 | 60 | 90 | 62 | 7.5 | 2925 | 3900 | 5850 | 4030 | FE, BE | Real-time event broadcasting integration risk
Phase 1: Core MVP | Layer 2: API Gateway & Security - APIM & Entra B2C Auth | 90 | 120 | 170 | 123 | 13.3 | 5850 | 7800 | 11050 | 7995 | SA, BE | B2C custom flows and APIM policies can be finicky
Phase 1: Core MVP | Layer 3: Compute - Transaction & Ledger Service (Core Banking) | 160 | 210 | 300 | 217 | 23.3 | 10400 | 13650 | 19500 | 14105 | BE | Idempotency logic and ledger integrity are high-risk areas
Phase 1: Core MVP | Layer 3: Compute - Configuration & Town Map Service | 45 | 60 | 85 | 62 | 6.7 | 2925 | 3900 | 5525 | 4030 | BE | Cosmos DB schema design relatively straightforward
Phase 1: Core MVP | Layer 3: Compute - Basic Gamification Progression Service | 45 | 60 | 90 | 62 | 7.5 | 2925 | 3900 | 5850 | 4030 | BE | Progression rules may expand based on JA feedback
Phase 1: Core MVP | Layer 3: Compute - Analytics & Reporting Service | 60 | 80 | 120 | 83 | 10 | 3900 | 5200 | 7800 | 5395 | BE, Data | Read-replica setup and BI formatting take iteration
Phase 1: Core MVP | Layer 4: Async Event-Bus - Azure Service Bus Provisioning | 35 | 50 | 75 | 52 | 6.7 | 2275 | 3250 | 4875 | 3380 | DevOps, BE | Message topic design needs careful upfront planning
Phase 1: Core MVP | Layer 5: Observability & Validation - QA, AppInsights, Deployment | 210 | 270 | 390 | 280 | 30 | 13650 | 17550 | 25350 | 18200 | QA, Sec, PM | Bug count varies heavily with integration scope
TOTAL | Phase 1 Sub-Total (Dev) | 1275 | 1680 | 2400 | 1733 | 56.4 | 82875 | 109200 | 156000 | 112645 |  | Combined PERT SD uses root-sum-of-squares
Phase 2: Nice to Have | Layer 1: Edge & UI - External Hardware SDK Integrations | 130 | 180 | 280 | 188 | 25 | 8450 | 11700 | 18200 | 12220 | FE, QA | NFC/ePOS SDK docs are often poorly maintained
Phase 2: Nice to Have | Layer 3: Compute - AI Integrations (Azure OpenAI) | 70 | 100 | 160 | 105 | 15 | 4550 | 6500 | 10400 | 6825 | BE, Designer | LLM prompt engineering requires many iterations
Phase 2: Nice to Have | Layer 3: Compute - True Offline Synchronization Logic | 70 | 100 | 170 | 107 | 16.7 | 4550 | 6500 | 11050 | 6955 | BE, FE, SA | Conflict resolution edge cases are notoriously complex
Phase 2: Nice to Have | Layer 3: Compute - Intricate Gamification & Supply Line Math | 90 | 130 | 200 | 135 | 18.3 | 5850 | 8450 | 13000 | 8775 | BE, QA | Logistics math requires extensive domain modeling
Phase 2: Nice to Have | Layer 3: Compute - Automated Dynamic PDF Generation Engine | 50 | 70 | 110 | 73 | 10 | 3250 | 4550 | 7150 | 4745 | FE, BE | PDF layout precision across devices adds edge cases
Phase 2: Nice to Have | Layer 5: Observability - Expanded Enterprise Environments | 30 | 40 | 65 | 42 | 5.8 | 1950 | 2600 | 4225 | 2730 | DevOps | Additional env provisioning is well-understood work
TOTAL | Phase 2 Sub-Total (Dev) | 440 | 620 | 985 | 650 | 40 | 28600 | 40300 | 64025 | 42250 |  | Combined PERT SD uses root-sum-of-squares
TOTAL | FULL SCOPE TOTAL (Dev Only) | 1715 | 2300 | 3385 | 2383 | 69.1 | 111475 | 149500 | 220025 | 154895 |  | Combined PERT SD uses root-sum-of-squares