## Sheet1
Phase | Feature (Module Area) | Hours | Cost | Team | Comments
Phase 1: Core MVP | Foundation - Requirements Analysis & Technical Discovery | 40 | 2600 | PM, SA | Mapping RFP requirements to System logic
| Foundation - Architecture & Database Schema Design | 30 | 1950 | SA | Designing Microservices topography
| Foundation - Azure Cloud Environment Setup & CI/CD Pipelines | 70 | 4550 | DevOps | 3 secure target environments (Dev, Staging, Prod)
| Foundation - Local Developer Testing Setup (Docker Compose) | 40 | 2600 | DevOps, BE | Containerized local-dev hooks for frictionless builds
| Layer 1: Edge & UI - UX Conceptualization, Visual Identity, WCAG 2.2 AA | 130 | 8450 | Designer, FE | Core flow designs
| Layer 1: Edge & UI - Student Tablet Mobile Application (PWA) | 260 | 16900 | FE | Core banking flows, Civic Voting Module, POS checkout UX, QR Scanning
| Layer 1: Edge & UI - Teacher & Volunteer Monitoring Dashboard | 80 | 5200 | FE | Real-time read-only oversight metrics
| Layer 1: Edge & UI - Admin Core: User Mgmt, Roles, Controls & Moderation Flows | 120 | 7800 | FE, BE | Secure CMS for Staff routing, localization, configuration moderation
| Layer 1: Edge & UI - Admin Automation: Real-time Event Controllers | 60 | 3900 | FE, BE | UI event creation dispatch (e.g. Town Hall, Tornado Alert triggers)
| Layer 2: API Gateway & Security - APIM (BFF) & Entra B2C Auth Setup | 120 | 7800 | SA, BE | Token auth, Rate Limiting, Zero Trust architecture
| Layer 3: Compute - Transaction & Ledger Service (Core Banking Engine) | 210 | 13650 | BE | SQL persistence, Idempotency tracking
| Layer 3: Compute - Configuration & Town Map Service | 60 | 3900 | BE | Cosmos DB configuration bindings
| Layer 3: Compute - Basic Gamification Progression Service (No AI) | 60 | 3900 | BE | Standard progression APIs (Integrates with Admin Controller triggers)
| Layer 3: Compute - Analytics & Reporting Service | 80 | 5200 | BE, Data | Read-replica historical reports
| Layer 4: Async Event-Bus - Azure Service Bus Provisioning | 50 | 3250 | DevOps, BE | Event choreography messaging infrastructure
| Layer 5: Observability & Validation - QA, Load Tests, App Insights, Store Deployment | 270 | 17550 | QA, Sec, PM | E2E bugs, Distributed Tracing integration
Phase 2: Nice to Have | Layer 1: Edge & UI - Extensive External Hardware SDK Integrations | 180 | 11700 | FE, QA | Physical NFC tags, ePOS Swipers, Radio Hook
| Layer 3: Compute - Cutting-Edge AI Integrations / Gateway Hook | 100 | 6500 | BE, Designer | Azure OpenAI business slogans, speech-to-text
| Layer 3: Compute - True Offline Synchronization Resolution Logic | 100 | 6500 | BE, FE, SA | Heavy conflict engine for extreme network outage
| Layer 3: Compute - Intricate Gamification & Supply Line Math | 130 | 8450 | BE, QA | Granular logistics depletion, real-time demand engines
| Layer 3: Compute - Automated Dynamic PDF Generation Engine | 70 | 4550 | FE, BE | Code-driven offline paper backups
| Layer 5: Observability & Scale - Expanded Enterprise Environments | 40 | 2600 | DevOps | Dedicated segregated QA cluster setup
| Sub-Total | 2300 | 149500
| PM (10%) | 230 | 14950
| Year 1 Support (Hyper-Care & Maintenance) | 1200 | 78000 | 1 FTE | Post-launch monitoring
| Total | 3730 | 242450
| Man Months | 15.8 |  |  | Based on 160h/month
Notes
These estimates represent the FULL Scope (Option A), categorised by the Microservices Architecture SDLC.
Total Core Dev Hours: 1680. Total Phase 2 / Optional Dev Hours: 620. Total: 2300 Dev Hours.
176.4706