## Realistic Estimate
Phase | Feature (Module Area) | Hours | Cost | Team | Comments / Q&A Reference
Phase 1: Core MVP | Foundation - Requirements Analysis & Technical Discovery and Mobile App POC, CMS POC and Dashboard POC | 320 | 27200 | PM, SA | RFP + Q&A review; user story mapping; acceptance criteria definition
| Foundation - Architecture & DB Schema (10-15K user scale) | 90 | 7650 | SA | Microservices topography; schema design for 60-70 concurrent simulations
| Foundation - Azure Cloud Env Setup & CI/CD Pipelines (3 envs) | 110 | 9350 | DevOps | Dev, Staging, Prod + branch preview envs; automated build, test, deploy
| Foundation - Local Developer Testing (Docker Compose service mesh) | 50 | 4250 | DevOps, BE | All services containerized; local seed data; dev onboarding < 1 day
| Foundation - Security Policy, Zero Trust & Key Vault Setup | 60 | 5100 | SA, DevOps | Managed Identities, internal mTLS, secret scanning, APIM threat policies
| Foundation - COPPA Data Anonymization Engine (30-day rule) | 50 | 4250 | BE, SA | Q110: Scheduled job anonymizes student data post-simulation
| User Experience Design (Design Thinking) | 800 | 68000 | Designer | To be reviewed and updated by Kyle
| UI - UX Research, User Flows & B&W Wireframes (all roles) | 180 | 15300 | Designer | Q79: B&W wireframe review before visual design; all 6+ student roles covered
| UI - Visual Design System, Style Guide, 2.5D Mood Boards | 200 | 17000 | Designer, FE | Q18/Q40: 2.5D/isometric; 3rd grade reading level; state-of-art for age 9-12
| UI - Core Tablet + Laptop App (Single PWA codebase, all states) | 380 | 32300 | FE | Q139/Q140: Portrait + landscape; tablet primary; laptop fallback; smooth UX
| UI - Student Role UIs: POS, Payroll, Banking, Loan, Billing, Voting | 290 | 24650 | FE | Q22/Q38: Distinct functional UIs per role; custom business graphic from CMS
| UI - Teacher & Volunteer Real-Time Monitoring Dashboard | 120 | 10200 | FE | Q24/Q48: Real-time business health; financial indicators; no forced-alert engine
| UI - Admin Core: User Mgmt, Roles, Permissions, Moderation | 170 | 14450 | FE, BE | Q37: Sim Managers, Volunteers, Educators, JA National with distinct permissions
| UI - Admin Live Event Controllers (Tornado Alert, Town Hall, Pause) | 90 | 7650 | FE, BE | Dispatch real-time simulation triggers to all connected tablets simultaneously
| UI - CMS Multi-Tenant: National Inheritance + Local Override + Clone | 320 | 27200 | FE, BE | Q6/Q128: Local precedence; clone/duplicate Areas; version history; rollback
| UI - Canva-Like Digital Marketing Tool (template + library + publish) | 200 | 17000 | FE, BE | Q13: Structured step-by-step; templates; text edit; image library; town display
| UI - CFO Real-Time Screen Sharing (14-20 concurrent biz sessions) | 130 | 11050 | FE, BE | Q14/Q131: Mirror CFO device via Azure Web PubSub; no audio; resilient on WiFi
| UI - DJ Radio Dashboard (Playlist control, Mic, A/V output) | 90 | 7650 | FE | Q17/Q45: Built-in DJ UI; wide A/V adaptability; live microphone announcements
| UI - Voting Module UI (Civic engagement per simulation schedule) | 60 | 5100 | FE | Students vote during simulation; real-time results; admin-triggered
| UI - Team Building & Onboarding Guided Flows | 60 | 5100 | FE | Q36/Q42: Business intro; first-time guided walkthroughs for POS/Loan/Billing
| UI - Sponsor Logo + Color + Branding Upload (per business via CMS) | 50 | 4250 | FE, BE | Q64: Logo, color, text override per business; no custom sponsor code
| UI - Business Scenarios: Ethical Dilemma UX & Donation Decision Flows | 80 | 6800 | FE | Q16: Character education UI; XP consequences displayed; CMS-configurable amounts
| UI - Post-Simulation Student & Teacher Reflection Report UI | 60 | 5100 | FE | Q48: Post-sim view for student self-reflection; educator review dashboard
| API - APIM BFF (routing, rate-limiting, tablet vs desktop payloads) | 90 | 7650 | SA, BE | Single entry; rate-limiting during peak shopping windows; payload transforms
| API - Entra B2C + Session-Based JWT Auth (per-device, no student PII) | 60 | 5100 | SA, BE | Q71/Q116: Session-auth per device; no individual student accounts or emails
| Business - Transaction & Ledger Service (50-100 TPS, Idempotency, ACID) | 360 | 30600 | BE | Q7/Q59: 500 txn/10-min; Redis idempotency; SQL ACID; debit + payroll + billing
| Business - Offline Local-First Queue + Sync + Conflict Resolution | 260 | 22100 | BE, FE, SA | Q7/Q15/Q133: Core requirement; queue locally; reconcile on reconnect; no-PII keys
| Business - Configuration & Town Map Service (Cosmos DB flexible schema) | 100 | 8500 | BE | Q31/Q62: Dynamic per-Area layouts; local Areas define businesses, roles, tasks
| Business - Business Scenarios & Character Education Engine | 140 | 11900 | BE | Q16: MANDATORY. Ethical dilemmas; XP consequences; donation CMS config amounts
| Business - Physical Debit Card Reader SDK Integration | 90 | 7650 | FE, BE | Q137: 3-digit account swipe → POS; existing production model; iOS + Android
| Business - Gamification + XP Engine (JA co-designed formula) | 130 | 11050 | BE | Q51: JA provides action list; formula built collaboratively with JA team
| Business - Reporting Service (in-app + PDF + Power BI export) | 190 | 16150 | BE, Data | Q72/Q122/Q123: Student, business, simulation reports; PDF shareable; BI-ready
| Business - Sponsor Tracking & Yearly Analytics Service | 80 | 6800 | BE, Data | Q127: Students per business; popular choices; sales prices; ad assets per Area
| Business - Notification & WebSocket Service (room-scoped events) | 80 | 6800 | BE, DevOps | Azure Web PubSub: town alerts; per-business updates; admin broadcast channel
| Business - Audit Log, Transaction Cancellation & Admin Override | 80 | 6800 | BE | Q111/Q121: Admin audit 30d; user actions 7d; admin-only txn cancel; log export
| Business - Disaster Recovery, Full Simulation State Save & Resume | 130 | 11050 | BE, DevOps | Q143: Full state resume mandatory; simulations CANNOT restart; RTO: 1-2 seconds
| Business - Voting Service (civic simulation ballot + results engine) | 80 | 6800 | BE | Real-time ballot processing; business-level and town-wide vote types
| Business - CMS Asset Pipeline (logo uploads, image library, CDN delivery) | 80 | 6800 | BE, DevOps | Q47/Q142: Sponsor logos; marketing image library; vendor dictates size/format
| Business - Payroll Engine (CFO submission, student salary credit) | 70 | 5950 | BE | Q101: Payroll = most software-intensive phase; CFO submits; distributes salaries
| Event Bus - Azure Service Bus Topics, Subscriptions & DLQ Handling | 80 | 6800 | DevOps, BE | Decouples banking from gamification, notifications, and reporting asynchronously
| QA - Automated Test Suite (unit, integration, regression, CI-gated) | 280 | 23800 | QA | All PRs trigger regression; banking + offline sync tests mandatory before merge
| QA - WCAG 2.2 AA (all interfaces) + 3rd-Party Audit Coordination | 130 | 11050 | QA, Designer | Q8/Q46: JA has external auditor; vendor remediates and supports VPAT completion
| QA - Security Hardening & Penetration Testing (OWASP Top 10) | 200 | 17000 | Sec, SA | Threat modelling, API fuzzing, zero-trust validation, student PII protection
| QA - Performance Engineering & 60-70 Concurrent Simulation Load Test | 220 | 18700 | QA, DevOps | Q125/Q126: 10-15K concurrent users; 50-100 TPS spikes; shopping period simulation
| QA - Cross-Device Testing (iPad, Android tablet, Chromebook, laptop) | 130 | 11050 | QA | Q112/Q114: Area-owned devices; no standardized hardware; wide OS + browser range
| QA - Offline & Network Degradation Testing | 130 | 11050 | QA, BE | Q115: 100 Mbps typical; validate local queue behavior under network interruption
| QA - User Acceptance Testing + Iterative Bug Fix Cycles | 180 | 15300 | QA, FE, BE | Structured UAT with JA advisory group + end users; 2 full UAT cycles minimum
| QA - Real-Time Sync & Transaction Conflict Stress Testing | 100 | 8500 | QA, BE | Q12: Frozen accounts; payroll + purchase contention; mid-transaction drops tested
| Delivery - App Store (iOS + Android) & MDM Distribution Setup | 90 | 7650 | PM, DevOps | Q74: App Store + MDM dual paths; Q83: JA provides Apple + Google Dev accounts
| Delivery - Admin CMS Guide + Simulation User Guide (non-tech JA staff) | 130 | 11050 | PM, SA | Q42/Q66: In-depth manuals; education-focused non-technical staff audience
| Delivery - Spanish Localization (vendor-provided per Q68) | 150 | 12750 | FE, Designer | Q68: JA expects vendor to provide all translated simulation content
| Delivery - Pilot On-Site Support (select JA Area live sessions) | 200 | 17000 | PM, QA, SA | Q77/Q78: Vendor on-site for select pilots; instant availability for remainder
| Delivery - Post-Pilot Remediation Sprint (10-15 JA Areas feedback) | 280 | 23800 | FE, BE, QA | Q9/Q81: Defects triaged vs enhancements; critical issues resolved pre-launch
| Delivery - DR Testing, Simulation State Recovery Validation | 80 | 6800 | QA, DevOps | Q143: Full walkthrough of failure + resume; verify no data loss or txn gaps
| Delivery - Go-Live Readiness & Stakeholder Sign-Off Coordination | 80 | 6800 | PM | Q9: JA USA product + program leadership + functional stakeholders sign-off
| Delivery - First-Week Post-Launch Hypercare (instant availability) | 60 | 5100 | PM, BE, QA | Q78: Vendor on-standby during first weeks of initial release
Phase 2: Nice to Have | AI - Slogan Generation (Azure OpenAI, scaffolded, 3-strike guardrails) | 150 | 12750 | BE, Designer | Q20/Q136: Guided structured generation; limited options; content moderation filter
| AI - CEO Speech-to-Text Transcription & In-Simulation Display | 100 | 8500 | BE, FE | Q20: Transcription only; student writes speech; system transcribes + displays
| NFC Tap-to-Pay (iOS + Android cross-platform + graceful QR code fallback) | 200 | 17000 | FE, QA | Q19/Q138: Nice-to-have; cross-platform NFC variability; graceful degradation
| Advanced Gamification - Inventory Depletion & Supply Chain Logistics | 180 | 15300 | BE, QA | Replaces unlimited stock assumption; real depletion math; demand-driven pricing
| Expanded Dedicated QA Environment (4th standalone regression cluster) | 50 | 4250 | DevOps | Isolated env for automated regression and load test pipelines
0
| Sub-Total Dev Hours (Phase 1 + Phase 2) | 9180 | 780300
| Contingency Buffer (10%) | 0 | 0
| PM / Delivery Management (11% of Dev+Contingency) | 1009.8 | 85833 |  | Weekly sessions, milestone reviews, stakeholder sign-offs, pre-reads per Q10
| Year 1 Support - Hyper-Care & Maintenance | 1200 | 102000 | 1 FTE | Q5: 100% uptime M-F 8AM-7PM ET; alerts allow JA to manage with vendor escalation planned for approx. 1 school year.
| GRAND TOTAL | 11389.8 | 968133 |  | Rate: $85/hr ¦ Budget Reference: $1M cap per Q25
Based on 160h/month
| Man Months (Full Engagement) | 71.19 |  |  | Including PM, and support
Notes
REALISTIC ESTIMATE ¦ Rate: $85/hr (blended) ¦ Dev: 9100 hrs
Y1 Support: 1200 hrs ¦ TOTAL: 11101.2 hrs ¦ TOTAL COST: $960,585
JA Confirmed Budget Cap: $1,000,000 (Q25) ¦ This estimate is within that cap.
|  | Blended Rate per Hour | 85
SCOPE NOTES:
- Includes ALL Phase 1 (Core MVP) + ALL Phase 2 (Optional) features
- Phase 1 mandatory items confirmed by Q&A: Business Scenarios (Q16), Offline Sync (Q7/Q133),
Canva Marketing Tool (Q13), CFO Screen Sharing (Q14), DJ Radio (Q17), Debit Card (Q137),
Data Anonymization (Q110), Spanish Localization (Q68), Voting Engine, Pilot Support (Q77)
- Phase 2 optional: AI Slogan/Speech (Q136), NFC (Q19), Advanced Supply Chain Math
- Paper fallback NOT included - not required if offline mode works (Q134)
- Budget cap confirmed at $1M for initial release (Q25)
- Hourly rate: $85/hr blended across all roles