## Revised Estimates
Phase | Feature (Module Area) | Hours | Cost (@ $85/hr) | Team | Comments / Q&A Reference
Phase 1: Core MVP | Foundation - Requirements Analysis & Technical Discovery | 50 | 4250 | PM, SA | Q2: Discovery largely done by JA; vendor refines execution per Q&A
| Foundation - Architecture & DB Schema (scaled to 10-15K users) | 70 | 5950 | SA | Q125/Q126: 60-70 concurrent simulations; design for horizontal scaling
| Foundation - Azure Cloud Env Setup & CI/CD Pipelines (3 envs) | 100 | 8500 | DevOps | Q57: JA provides Azure tenant; vendor owns pipeline config & permissions
| Foundation - Local Developer Testing Setup (Docker Compose) | 40 | 3400 | DevOps, BE | Full service mesh containerized locally for all developers
| Foundation - Security Policy, Key Vault & Zero Trust Setup | 40 | 3400 | SA, DevOps | Managed Identities, internal mTLS, secret scanning in CI
| Foundation - Data Anonymization Engine (COPPA 30-day rule) | 40 | 3400 | BE, SA | Q110: Anonymize student data after 30 days post-simulation
| Layer 1: UI - UX Research, User Flows & Wireframes (all roles) | 160 | 13600 | Designer | Q79: B&W wireframes per JA review process; all functional roles covered
| Layer 1: UI - Visual Design System, Style Guide, Mood Boards | 160 | 13600 | Designer, FE | Q18: 2.5D/isometric TBD; Q40: 3rd grade reading level; age-appropriate
| Layer 1: UI - Core Tablet & Laptop App (Single PWA codebase) | 320 | 27200 | FE | Q139: One app; Q140: portrait and landscape; tablets + laptops supported
| Layer 1: UI - Student Role UIs (POS, Payroll, Banking, Loan, Billing, Voting) | 240 | 20400 | FE | Q22/Q38: Role UIs differ by function; custom business graphic per CMS
| Layer 1: UI - Teacher & Volunteer Real-Time Monitoring Dashboard | 100 | 8500 | FE | Q24/Q48: Real-time business health; simple visual indicators; no rules engine
| Layer 1: UI - Admin Core: User Mgmt, RBAC, Simulation Moderation | 150 | 12750 | FE, BE | Q37: Sim Managers, Volunteers, Educators, JA National as distinct roles
| Layer 1: UI - Admin Live Event Controllers (Tornado Alert, Town Hall) | 70 | 5950 | FE, BE | Staff dispatches live simulation events to all connected tablets
| Layer 1: UI - CMS Multi-Tenant National/Local Inheritance (clone/duplicate) | 280 | 23800 | FE, BE | Q6/Q128: Local overrides take precedence; clone Area configs; version control
| Layer 1: UI - Canva-Like Digital Marketing Tool (template + publish) | 160 | 13600 | FE, BE | Q13/Q135: Step-by-step mission, templates, text, image library, display in town
| Layer 1: UI - CFO Real-Time Screen Sharing (14-20 concurrent business sessions) | 100 | 8500 | FE, BE | Q14/Q131: Mirror CFO to teammates via Azure Web PubSub; no audio narration
| Layer 1: UI - DJ Radio Dashboard (Playlist, Mic Announcements, A/V out) | 80 | 6800 | FE | Q17/Q45: Bluetooth to built-in speakers; wide A/V variety; microphone for DJ
| Layer 1: UI - Contextual In-App Guided Flows (POS, Loan, Billing first use) | 60 | 5100 | FE | Q42/Q107: First-time guided step-by-step; no extensive system onboarding
| Layer 1: UI - Sponsor Logo & Branding Upload via CMS | 40 | 3400 | FE, BE | Q64: Logo, colors, business name text override; no custom sponsor code
| Layer 2: API - APIM BFF (routing, rate-limiting, payload transforms) | 80 | 6800 | SA, BE | Single entry point; tablet vs desktop payload optimization; rate-limiting
| Layer 2: API - Entra B2C Auth + JWT + Session Token (per-device auth) | 50 | 4250 | SA, BE | Q71/Q116: Session-based students; simpler auth; no individual student accounts
| Layer 3: Compute - Transaction & Ledger Service (50-100 TPS, Idempotency) | 320 | 27200 | BE | Q7/Q59: 500 events per 10-min window; Redis idempotency key; ACID SQL
| Layer 3: Compute - Offline Local-First Queue & Reconciliation Engine | 220 | 18700 | BE, FE, SA | Q7/Q133: Core requirement; queue locally; sync + reconcile on reconnect
| Layer 3: Compute - Configuration & Town Map Service (Cosmos DB) | 80 | 6800 | BE | Q31/Q62: Unique per Area; local Areas create new workflows and job roles
| Layer 3: Compute - Business Scenarios & Character Education Engine | 110 | 9350 | BE | Q16: MANDATORY for grant funding. Ethical dilemmas, XP consequences
| Layer 3: Compute - Physical Debit Card Reader SDK Integration | 80 | 6800 | FE, BE | Q137: 3-digit account number swiped to populate POS; currently in production
| Layer 3: Compute - Gamification + XP Engine (JA rules, collaborative formula) | 100 | 8500 | BE | Q51: JA provides action list; vendor + JA co-design XP formula
| Layer 3: Compute - Reporting Service (in-app + PDF export + Power BI ready) | 160 | 13600 | BE, Data | Q72/Q122/Q123: Student, business, simulation-level reports; PDF shareable
| Layer 3: Compute - Sponsor Tracking & Yearly Analytics | 60 | 5100 | BE, Data | Q127: Track students per business, popular options, sales prices, ad assets
| Layer 3: Compute - Notification & WebSocket Service (town-scoped events) | 70 | 5950 | BE, DevOps | Azure Web PubSub: admin broadcasts, alerts, per-business live updates
| Layer 3: Compute - Audit Log & Transaction Cancellation (Admin only) | 60 | 5100 | BE | Q111/Q121: Admin audit 30d; user actions 7d; admin can cancel sim transactions
| Layer 3: Compute - Disaster Recovery & Full Simulation State Resume | 120 | 10200 | BE, DevOps | Q143: Full state recovery mandatory; simulation resumes exact prior state
| Layer 3: Compute - Data Pipeline & CMS Asset Management | 100 | 8500 | BE, DevOps | Q47/Q142: JA Area sponsor logo uploads; vendor defines size + format specs
| Layer 4: Event Bus - Azure Service Bus Topics & Dead-Letter Handling | 70 | 5950 | DevOps, BE | Decouples banking from gamification, reporting, and notification pipelines
| Layer 5: QA - Automated Test Suite (unit, integration, regression, CI-gated) | 280 | 23800 | QA | CI-gated; every PR triggers regression; full coverage on banking + sync
| Layer 5: QA - WCAG 2.2 AA + 3rd-Party Audit Coordination | 100 | 8500 | QA, Designer | Q8/Q46: JA has external auditor; vendor supports VPAT and remediation cycles
| Layer 5: QA - Security Hardening & Penetration Testing (OWASP Top 10) | 160 | 13600 | Sec, SA | Threat modelling, zero-trust validation, API fuzzing, secrets audit
| Layer 5: QA - Performance Engineering & 60-70 Concurrent Simulation Load Test | 200 | 17000 | QA, DevOps | Q125/Q126: 10-15K users; shopping period spike testing (50-100 TPS)
| Layer 5: QA - User Acceptance Testing + Bug Fix Cycles | 180 | 15300 | QA, FE, BE | Structured UAT with JA advisory group + pilot participants
| Layer 5: QA - Cross-Device & Offline Degradation Testing | 100 | 8500 | QA, BE | Q112/Q114/Q115: iPad, Android tablet, Chromebook, laptop; degraded-mode check
| Layer 5: QA - Real-Time Sync & Transaction Conflict Stress Tests | 60 | 5100 | QA, BE | Q12: Frozen accounts, payroll + purchase contention, mid-tx network drop
| Layer 5: Delivery - App Store (iOS + Android) & MDM Distribution | 80 | 6800 | PM, DevOps | Q74: Both App Store + MDM; Q83: JA provides Apple + Google dev accounts
| Layer 5: Delivery - CMS User Guide + Simulation User Guide (non-technical JA staff) | 100 | 8500 | PM, SA | Q42/Q66: In-depth manuals; JA staff are education-focused not technical
| Layer 5: Delivery - Spanish Localization (vendor provided per Q68) | 130 | 11050 | FE, Designer | Q68: JA expects vendor to provide translated content
| Pilot - On-Site Support (select JA Area live simulation sessions) | 160 | 13600 | PM, QA, SA | Q77: Vendor expected in-person for select pilots; instant availability for rest
| Pilot - Post-Pilot Remediation Sprint (10-15 JA Area feedback resolution) | 280 | 23800 | FE, BE, QA | Q9/Q81: Structured sprint; defects vs enhancements triaged per governance
Phase 2: Nice to Have | AI - Slogan Generation (Azure OpenAI, scaffolded, 3-strike guardrails) | 120 | 10200 | BE, Designer | Q20/Q136: Flexible for pilot; guided; constrained outputs; age-appropriate
| AI - CEO Speech-to-Text Transcription & In-Simulation Display | 80 | 6800 | BE, FE | Q20: Transcription only; student writes own speech; system records/displays
| NFC Tap-to-Pay (iOS + Android + graceful QR code fallback) | 160 | 13600 | FE, QA | Q19/Q138: Confirmed nice-to-have; cross-platform NFC hardware variability
| Advanced Gamification - Inventory Depletion & Supply Chain Math | 140 | 11900 | BE, QA | Replaces unlimited stock assumption with real depletion logistics engine
| Expanded QA Environment (4th dedicated regression cluster) | 40 | 3400 | DevOps | Dedicated cluster separate from Dev/Staging/Prod for isolated load testing
| Sub-Total Dev Hours | 6310 | 536350
| PM / Delivery Management (11%) | 694 | 58990 |  | Weekly working sessions, milestone reviews, pre-reads, stakeholder sign-offs per Q10/Q89
| Year 1 Support - Hyper-Care & Maintenance | 1200 | 102000 | 1 FTE | Q5: 100% uptime M-F 8AM-7PM ET; alerts + monitors enable JA to handle incidents with vendor escalation
| Year 2 Support - Maintenance & Annual Enhancements | 600 | 51000 | 0.5 FTE | Annual upgrade cycle per RFP; infrastructure health; minor feature additions
| Total | 8804 | 748340 |  | Budget Target: $750,000 ¦ Actual: $748,340
| Man Months (Dev Only) | 39.4 |  |  | Based on 160h/month
| Man Months (Full Engagement) | 55 |  |  | Including PM and support years
Notes
REVISED ESTIMATES ¦ Rate: $85/hr ¦ Dev: 6310 hrs ¦ PM: 694 hrs ¦ Support: 1800 hrs ¦ TOTAL: 8804 hrs ¦ COST: $748,340
Built from comprehensive review of all 143 Q&A responses from JA BizTown RFP.
ITEMS MOVED INTO PHASE 1 BASED ON Q&A::
[Q16] Business Scenarios / Character Education = MANDATORY (grant-funded requirement)
[Q7/Q15/Q133] Offline Local-First Queue + Sync Engine = REQUIRED by JA
[Q13/Q135] Canva-Like Digital Marketing Tool = confirmed MVP scope
[Q14/Q131] CFO Real-Time Screen Sharing = required feature (14-20 concurrent)
[Q17/Q45] DJ Radio Dashboard = required (replaces fragmented A/V approach)
[Q137] Physical Debit Card Reader = current production integration
[Q110] Data Anonymization 30-day = COPPA compliance
[Q68] Spanish Localization = vendor to provide
[Q77/Q9] Pilot On-Site Support + Post-Pilot Sprint = vendor commitment
CONFIRMED PHASE 2 / OPTIONAL:
[Q136] AI features (slogan + speech-to-text) = flexible, can slip past pilot
[Q19/Q138] NFC = nice-to-have, graceful QR fallback required
[Q134] Paper fallback = not required if offline mode works
[Q25] Budget confirmed: $1M cap for initial release