## Sheet1
Phase | Feature | Hours | Cost | Team | Comments
Discovery and Design | Requirements Analysis Technical Discovery | 240 | 21600 | PM, SA, SSE
| UX/UI Conceptualization & Mood Boards Wireframes & Clickable Prototyping Visual Identity | 320 | 28800 | Designer, FE | Designer Full Time
| System Architecture Database Schema Design Azure Subscriptions Network & Governance Setup CI/CD Pipelines 4 Environments (Dev, QA, Staging, Prod) | 150 | 13500 | DevOps, SA | Terraform/ARM Infrastructure
Development | Backend Core Simulation Engine Financial Engine Auth Entra B2C | 400 | 36000 | BE
| Loan Management Check Deposit Shopping Mode Emergency Mode Rule Engine | 800 | 72000
| Backend Gamification API Engine Azure OpenAI Integration | 160 | 14400 | BE
| CMS: Multi-Tenant Admin Templates Localization React UI Offline PDF Gen | 350 | 31500 | FE, BE
| Mobile Apps: Student App SPA Onboarding Financial App UI AI Tools POS Hardware (NFC/ePOS/Swipers) | 600 | 54000 | FE | React Native / Expo
| Web/Tablet Dashboards: Staff Teacher & Volunteer | 360 | 32400 | FE, BE
| Reporting & Power BI Analytics Data | 160 | 14400 | Data, BE
Testing & Delivery | Accessibility Validation (WCAG 2.2 AA) Load Testing Security Assessments | 160 | 14400 | QA, Sec
| End-to-End User Acceptance Iterative Bug Fixes | 80 | 7200 | QA, FE, BE
| App Store Processing Final Code Reviews Data Schema Manuals Admin Training | 90 | 8100 | PM, SA, DevOps
0
| Sub-Total | 3870 | 348300
| PM (10%) | 387 | 34830
| Total | 4257 | 383130
Notes
These estimates account for the complete set of RFP requirements.
Includes complex AI integrations, Gamification engine APIs, and 4 environment setups.
Assumes fully offline dynamic configurable PDFs generator.
Explicitly includes SDK connections for physical NFC usage and external ePOS debit card swipers.
|  | Blended Rate / Hour | 90