## Estimates
Phase | Feature | Hours | Cost | Team | Comments
Discovery and Design | Stakeholder Alignment & Data Mapping: Mapping HIDOE PTP, UH Banner SIS, and DLIR LMI datasets. Architecture & Security Design: Designing the "Zero-PII" Scrubber and Azure Government Cloud setup. | 720 | 46800 | PM, SA, Designer | Designer Full Time, PM and SA Provide Direction
| DevOps pipelines (CI/CD for Azure, 4 envs) | 80 | 5200 | DevOps | DevOps Owns, SA Directs
| UX/UI and Accessibility (WCAG 2.1 level AA) | 420 | 27300 | FE | FE Owns, PM/SA Directs
| Security, MFA, audit, compliance | 120 | 7800 | SA | SA to Deliver involving 1 BE
| Secure HIPAA-Compliant Cloud Setup (Dev, Test, UAT, Prod) Automated CI/CD Pipelines for Data & Code | 460 | 29900 | DevOps, BE and SA | DevOps Full Time, BE works on Workflows, Message Queues, Data Mapping, SA Provides direction
Development | Data Ingestion Pipelines: Building ETL/API connectors for HIDOE PTP, Banner, and DLIR batch/real-time feeds. | 1800 | 117000 | FE, BE, Designer and QA | FE, BE Full time, Designer as needed and QA part time - iteration testing
| AI Engine & RAG Implementation: Developing the LLM logic, RAG over UH catalogs, and CIP-SOC mapping. | 1200 | 78000
| Front-End PWA Development: Building the student portal, advisor dashboard, and mobile-optimized interfaces. | 1600 | 104000
| XAI & Analytics Dashboard: Building the explainability modules and administrative reporting suite. | 700 | 45500
| Episode-of-Care & Price Standardization Logic Risk Adjustment Modeling (Elixhauser, CMS-HCC) Role-Based Access Control (RBAC) & Site-Specific Logic Dashboard Development & Tableau Integration Export Services (Standard Analytic Files - SAFs) | 4300 | 279500 | FE, BE, Designer and QA | FE, BE Full time, Designer as needed and QA part time - iteration testing
Testing & Delivery | E2E Testing & Accessibility Audit: Full system integration testing, performance tuning, and ADA remediation. | 900 | 58500 | QA | QA Owns, PM and SA Direct
| Security Hardening & Pentesting: Final security audit, SOC 2 compliance check, and production deployment. | 420 | 27300
| Architecture documentation (network + topology) | 120 | 7800 | SA | SA to Deliver
| Technical Documentation & Training: SOPs, Admin Guides, and "Train-the-Trainer" sessions for counselors. | 160 | 10400 | PM and SA
| Hardening full System for UAT, Planning for Go-Live. Go-Live​ | 400 | 26000 | FE, BE, Designer, QA, PM, SA, DevOps | FE, BE Full time, Designer as needed and QA part time - iteration testing, PM and SA for Direction, DevOps for any last minute tweaks
| Sub- Total | 12060 | 783900
| PM | 1206 | 78390
| Year 1 Support (Hyper-Care & Maintenance: Post-launch monitoring, quarterly model retraining, and DLIR data refreshes.) | 2400 | 156000 | 2 - FTE(for continuous compliance and SLA management).
| Year 2 Support (Hyper-Care & AI Tuning) | 2400 | 156000 | 1.5 FTE (Data Eng, AI Eng, PM) | Refining the CIP-SOC Crosswalk based on real student outcomes and retraining models with the first year of live UHCC usage data.
| Year 3 Support (Steady State Ops) | 1800 | 117000 | 1 - FTE (Full-Stack, DevOps) | LMI Refresh: Quarterly updates of Hawaii Department of Labor salary/growth data. Ensuring WCAG 2.1 AA compliance persists through browser updates.
| Year 4 Support (Strategic Expansion) | 1800 | 117000 | 1.0 FTE (Full-stack, SA) | New Integration Points: Adding any new HIDOE or UHCC data nodes (e.g., specific campus-level internship feeds) that emerged since Go-Live.
| Year 5 (Optimization and Transition) | 20000 | 1300000 | 1.2 FTE (PM, SA, Data Engineer) | Transition Readiness: Preparing the "Model Weights" and "Data Sovereignty" package for handover (as per Q&A #41/42) if the contract ends.
| Total | 15666 | 1018290
| Man Months | 112
FTE
| Team | 0.5
| PM | 0.5
| Solution Architect | 0.5
| Front End Dev | 2
| BackEnd Dev | 3
| DBA | 0.5
| QA | 2
| Designer | 1
| DevOps | 0.5
10
| Total Capacity Hours Available, excluding Support | 19200
| Total Development Hours | 12060 |  | 1507.5
| Available Buffer Time to deal with Contingencies | 7140