## Sheet1
Phase | Feature | Hours | Cost | Team | Comments
Discovery and Design | Requirements Analysis & Technical Discovery | 40 | 4800 | PM, SA | Skipped Discovery for Luxury Items
| UX/UI Conceptualization, Wireframes & Visual Identity (Core Only) | 130 | 15600 | Designer, FE | No AI Interfaces, No Advanced Gamification Visuals
| System Architecture & Database Schema Design | 30 | 3600 | SA
Development | Azure Setups, CI/CD, 3 Environments (Dev, Staging, Prod) | 90 | 10800 | DevOps, SA | Removed QA Env
| Backend Core Simulation Engine, Financial Engine, Auth | 210 | 25200 | BE | Unlimited Inventory Assumption
| Backend Gamification API Engine (Simpler XP) | 60 | 7200 | BE | No AI Scenario Generation
| CMS: Admin, Templates, Localization, React UI | 280 | 33600 | FE, BE | Removed code-generated PDF engine
| Mobile Apps: Student App SPA, Core Financial App UI | 280 | 33600 | FE | No Deep Offline resolution, No A/V Integration, No Hardware APIs
| Web/Tablet Dashboards: Staff, Teacher & Volunteer | 190 | 22800 | FE, BE
| Reporting & Power BI Analytics Data | 110 | 13200 | Data, BE | Less Complex Historic Views
Testing & Delivery | Accessibility Validation (WCAG 2.2 AA), Load Testing, Security Assessments | 120 | 14400 | QA, Sec | Lighter load with fewer modules
| End-to-End User Acceptance Iterative Bug Fixes | 60 | 7200 | QA, FE, BE
| App Store Processing, Final Code Reviews, Training | 80 | 9600 | PM, SA, DevOps
0
| Sub-Total | 1680 | 201600
| PM (10%) | 168 | 20160
| Year 1 Support (Hyper-Care & Maintenance) | 1200 | 144000 | 1 - FTE
| Total | 3048 | 365760
Notes
These optimized estimates defer 'nice-to-have' luxury items.
Reductions applied: Omitting AI generation (Slogans/Speech-to-text), removing deep offline conflict sync.
Reductions applied: Removing A/V hardware integrations, physical radio stations, replacing dynamic PDF engine with static downloads.
Reductions applied: Assuming unlimited stock, avoiding complex supply-chain inventory backend logic.
Reductions applied: Defers physical external ePOS (debit card swipers/NFC readers) to Phase 2. Payment natively utilizes tablet camera QR scanning instead.