## Sheet1
Phase | Feature | Hours | Cost | Team | Comments
Phase 1: Core MVP | System Architecture & Setup: 3 environments, Core Cloud Setup | 120 | 7800 | SA, DevOps | Infrastructure Design + CI/CD
| UX/UI Conceptualization & Prototyping: Core flows, WCAG 2.2 AA | 130 | 8450 | Designer, FE | No Generative AI visuals
| Backend Core Simulation & Financial Engine: Basic Banking, Ledgers, APIs | 210 | 13650 | BE | Entra B2C Auth, Unlimited Inventory Assumption
| CMS & Multi-Tenant Administration: React UI for Staff, Static Template downloads | 280 | 18200 | FE, BE
| Mobile Apps & Web Dashboards: Student React Native SPA, Teacher Dashboard | 470 | 30550 | FE, BE | Tablet Camera QR usage
| Gamification Core & Basic Reporting: Simple Progression API, Historical BI Views | 170 | 11050 | BE, Data
| Testing, Delivery, & App Store: E2E, Bug Fixes, Accessibility Auditing | 300 | 19500 | QA, Sec, PM
Phase 2: Nice to Have / Optional | Extensive External Hardware SDK Integrations | 180 | 11700 | FE, QA | Physical NFC tags, ePOS Swipers, Radio Hook
| Intricate Gamification & Supply Line Math | 130 | 8450 | BE, QA | Granular logistics depletion, real-time demand engines
| Cutting-Edge AI Integrations | 100 | 6500 | BE, Designer | Azure OpenAI business slogans, speech-to-text
| Deep Offline Synchronization Logic | 100 | 6500 | BE, FE, SA | Conflict Resolution over unstable facility LAN
| Automated Dynamic PDF Generation | 70 | 4550 | FE, BE | Code-driven offline paper backups
| Expanded Enterprise Environments | 40 | 2600 | DevOps | Dedicated QA testing stacks
| Sub-Total | 2300 | 149500
| PM (10%) | 230 | 14950
| Year 1 Support (Hyper-Care & Maintenance) | 1200 | 78000 | 1 FTE | Post-launch monitoring
| Total | 3730 | 242450
| Man Months | 15.8 |  |  | Based on 160h/month
Notes
These estimates account for ALL requirements strictly as outlined in the RFP.
Both Phase 1 (MVP) and Phase 2 (Optional) items are delivered.
Includes AI, Gamification depth, true offline sync, hardware SDKs, and dynamic PDFs.