## Sheet1
Phase | Feature (Module Area) | Hours | Cost | Team | Comments
Phase 1: Core MVP | Foundation - Requirements Analysis & Technical Discovery | 40 | 2600 | PM, SA | Q2: Discovery substantially done by JA -- vendor refines execution
| Foundation - Architecture & Database Schema Design | 40 | 2600 | SA | Q125/Q126: Must support 10-15K concurrent users / 60-70 parallel simulations
| Foundation - Azure Cloud Env Setup & CI/CD Pipelines (3 Envs) | 80 | 5200 | DevOps | Q57: JA will work with vendor to deploy architecture into JA environment
| Foundation - Local Developer Testing Setup (Docker Compose) | 40 | 2600 | DevOps, BE | Containerized local-dev hooks for frictionless developer builds
| Foundation - Data Anonymization Engine (30-day COPPA rule) | 30 | 1950 | BE, SA | Q110: Anonymization process required after simulation reaches 30 days
| Layer 1: UI - UX Conceptualization, Style Tiles, WCAG 2.2 AA | 130 | 8450 | Designer, FE | Q18: 2.5D or isometric, TBD. Q40: 3rd grade reading level. Mood boards required
| Layer 1: UI - Core Tablet + Laptop App (Single Codebase PWA) | 280 | 18200 | FE | Q139: Single app, tablet primary; Q140: portrait AND landscape support
| Layer 1: UI - Student Role UIs (POS, Payroll, Banking, Billing, Voting) | 160 | 10400 | FE | Q22/Q38: Different UIs per role function (POS, CFO Payroll, etc.) not visual themes
| Layer 1: UI - Teacher & Volunteer Real-Time Monitoring Dashboard | 80 | 5200 | FE | Q24/Q48: Real-time business health visibility - No alert rules engine needed
| Layer 1: UI - Admin Core: User Mgmt, Roles, Moderation & Controls | 120 | 7800 | FE, BE | Q37: Simulation Managers, Volunteers, Educators as distinct roles
| Layer 1: UI - Admin Automation: Real-time Event Controllers (Town Hall, Tornado) | 60 | 3900 | FE, BE | Staff controls for live simulation event dispatch to all tablets
| Layer 1: UI - CMS National + Local Config (Inheritance Model) | 200 | 13000 | FE, BE | Q6/Q128: Local Area inherits national config. Local overrides take precedence
| Layer 1: UI - Canva-Like Digital Marketing Tool (Template-based) | 120 | 7800 | FE, BE | Q13/Q135: Step-by-step mission, templates, text edit, image library, publish/display
| Layer 1: UI - CFO Real-Time Screen Sharing (14-20 concurrent sessions) | 80 | 5200 | FE, BE | Q14/Q131: Mirror CFO device to teammates; no audio. Azure Web PubSub
| Layer 1: UI - DJ Radio Dashboard (Playlist, Mic Announcements) | 60 | 3900 | FE | Q17: Built-in DJ UI; plays to A/V system; wide variety of setups supported
| Layer 2: API Gateway - APIM, Entra B2C Auth (Session-based Students) | 100 | 6500 | SA, BE | Q71/Q116: Students are session-based. Simpler auth. Q60: Vendor manages CI/CD perms
| Layer 3: Compute - Transaction & Ledger Service (50-100 TPS capable) | 240 | 15600 | BE | Q7/Q59: 500 transactions per 10-min window; 50-100 TPS; Idempotency critical
| Layer 3: Compute - Offline Local-First Queue & Sync Engine | 150 | 9750 | BE, FE, SA | Q7/Q15/Q133: Explicitly required. Queue transactions locally, sync on reconnect
| Layer 3: Compute - Configuration & Town Map Service (Cosmos DB) | 70 | 4550 | BE | Q31/Q62: Businesses and job roles are unique per Area. Local Areas create new workflows
| Layer 3: Compute - Business Scenarios & Character Education Engine | 90 | 5850 | BE | Q16: MUST be MVP - grant-funded requirement. Ethical dilemmas, XP consequences
| Layer 3: Compute - Physical Debit Card Reader Integration | 70 | 4550 | FE, BE | Q137: Current system uses physical debit cards coded with 3-digit account numbers
| Layer 3: Compute - Gamification & XP Engine (with JA-defined rules) | 80 | 5200 | BE | Q51: JA provides actions, vendor designs formula collaboratively
| Layer 3: Compute - Reporting Service (In-app + PDF + CMS Export) | 100 | 6500 | BE, Data | Q72/Q122/Q123: In-app dashboards, PDF reports, export for Power BI
| Layer 3: Compute - Sponsor Tracking & Analytics Service | 40 | 2600 | BE, Data | Q127: Track students per business, sales prices, marketing assets per sponsor
| Layer 4: Async Event-Bus - Azure Service Bus (transactions, events) | 50 | 3250 | DevOps, BE | Decouples banking from gamification, notifications, and reporting
| Layer 5: Observability - App Insights, Distributed Tracing, DR State Recovery | 60 | 3900 | DevOps, BE | Q143: Full state recovery after failure; simulations resume from exact prior state
| Layer 5: Testing - QA, WCAG Audit (3rd party), Load to 10-15K users | 180 | 11700 | QA, Sec | Q8/Q46: JA has 3rd-party auditor. Load testing for 60-70 concurrent simulations
| Layer 5: Delivery - App Store (iOS/Android), MDM compat, JA User Training Manuals | 90 | 5850 | PM, SA, DevOps | Q74: App store + MDM dual distribution. Q42: Admin CMS + Simulation user guides
Phase 2: Nice to Have | AI - Slogan Generation (Azure OpenAI, 3-strike guardrails) | 100 | 6500 | BE, Designer | Q20/Q136: Guided scaffolded generation. Age-appropriate. Flexible for pilot
| AI - CEO Speech-to-Text Transcription & Display | 60 | 3900 | BE, FE | Q20: Transcription only (not AI writing). Student expression support
| Layer 1: UI - NFC Tap-to-Pay Integration (iOS + Android cross-platform) | 130 | 8450 | FE, QA | Q19/Q138: Nice-to-have. Cross-platform NFC + graceful QR fallback
| Layer 3: Compute - Advanced Gamification & Supply Chain Depletion Math | 100 | 6500 | BE, QA | Complex depletion logistics beyond unlimited stock assumption
| Layer 5: Observability - Expanded Dedicated QA Environment | 40 | 2600 | DevOps | 4th segregated environment beyond Dev/Staging/Prod
| Sub-Total Dev | 3270 | 212550
| PM (10%) | 327 | 21255
| Year 1 Support (Hyper-Care & Maintenance) | 1200 | 78000 | 1 FTE | Post-launch monitoring
| Total | 4797 | 311805 |  | NOTE: $1M budget cap per Q&A #25
| Man Months | 22.5 |  |  | Based on 160h/month
Notes
UPDATED based on full Q&A review (143 questions).
Key changes: Business Scenarios moved to Phase 1 (Q16 - grant requirement).
Offline Local-First Sync moved to Phase 1 (Q7/Q133 - JA explicitly required).
Added: Canva Digital Marketing Tool (Q13), CFO Screen Sharing (Q14), DJ Radio (Q17).
Added: Physical Debit Card Reader (Q137), Data Anonymization 30-day (Q110).
Added: Sponsor Tracking Service (Q127), 10-15K concurrent user load testing (Q125).
BUDGET CONSTRAINT: JA confirmed $1M cap for initial release (Q25).