## Sheet1
Phase | Feature (Module Area) | Hours | Cost | Team | Comments
Phase 1: Core MVP | Foundation - Requirements Analysis & Technical Discovery | 40 | 2600 | PM, SA | Mapping RFP requirements to System logic
| Foundation - Architecture & Database Schema Design | 30 | 1950 | SA | Designing Microservices topography
| Foundation - Azure Cloud Environment Setup & CI/CD Pipelines | 70 | 4550 | DevOps | 3 secure target environments (Dev, Staging, Prod)
| Foundation - Local Developer Testing Setup (Docker Compose) | 40 | 2600 | DevOps, BE | Containerized local-dev hooks for frictionless builds
| Layer 1: Edge & UI - UX Conceptualization, Visual Identity, WCAG 2.2 AA | 130 | 8450 | Designer, FE | Core flow designs
| Layer 1: Edge & UI - Student Tablet Mobile Application (PWA) | 260 | 16900 | FE | Core banking flows, POS checkout UX, QR Code Scanning
| Layer 1: Edge & UI - Teacher & Volunteer Monitoring Dashboard | 80 | 5200 | FE | Real-time read-only oversight metrics
| Layer 1: Edge & UI - JA Staff CMS & Admin Portal | 180 | 11700 | FE, BE | Staff routing, localization, configs
| Layer 2: API Gateway & Security - APIM (BFF) & Entra B2C Auth Setup | 120 | 7800 | SA, BE | Token auth, Rate Limiting, Zero Trust architecture
| Layer 3: Compute - Transaction & Ledger Service (Core Banking Engine) | 210 | 13650 | BE | SQL persistence, Idempotency tracking
| Layer 3: Compute - Configuration & Town Map Service | 60 | 3900 | BE | Cosmos DB configuration bindings
| Layer 3: Compute - Basic Gamification Progression Service (No AI) | 60 | 3900 | BE | Standard progression APIs
| Layer 3: Compute - Analytics & Reporting Service | 80 | 5200 | BE, Data | Read-replica historical reports
| Layer 4: Async Event-Bus - Azure Service Bus Provisioning | 50 | 3250 | DevOps, BE | Event choreography messaging infrastructure
| Layer 5: Observability & Validation - QA, Load Tests, App Insights, Store Deployment | 270 | 17550 | QA, Sec, PM | E2E bugs, Distributed Tracing integration
| Sub-Total | 1680 | 109200
| PM (10%) | 168 | 10920
| Year 1 Support (Hyper-Care & Maintenance) | 1200 | 78000 | 1 FTE | Post-launch monitoring
| Total | 3048 | 198120
| Man Months | 11.6 |  |  | Based on 160h/month
Notes
These estimates represent the core MVP ONLY (Option B), strictly categorised by the essential Azure Microservices.
Mobile App, Staff Portals, and SDLC processes are distinctly itemized for transparency.