## Sheet1
Phase | Feature (Module Area) | Hours | Cost | Team | Comments
Phase 1: Core MVP | Foundation - Requirements Analysis & Technical Discovery | 40 | 2600 | PM, SA | Mapping RFP requirements to System logic
| Foundation - Architecture & Database Schema Design | 30 | 1950 | SA | Designing Microservices topography
| Foundation - Azure Cloud Environment Setup & CI/CD Pipelines | 70 | 4550 | DevOps | 3 secure target environments (Dev, Staging, Prod)
| Foundation - Local Developer Testing Setup (Docker Compose) | 40 | 2600 | DevOps, BE | Containerized local-dev hooks for frictionless builds
| Layer 1: Edge & UI - UX Conceptualization, Visual Identity, WCAG 2.2 AA | 130 | 8450 | Designer, FE | Core flow designs
| Layer 1: Edge & UI - Student Tablet Mobile Application (PWA) | 260 | 16900 | FE | Core banking flows, Civic Voting Module, POS checkout UX, QR Scanning
| Layer 1: Edge & UI - Teacher & Volunteer Monitoring Dashboard | 80 | 5200 | FE | Real-time read-only oversight metrics
| Layer 1: Edge & UI - Admin Core: User Mgmt, Roles, Controls & Moderation Flows | 120 | 7800 | FE, BE | Secure CMS for Staff routing, localization, configuration moderation
| Layer 1: Edge & UI - Admin Automation: Real-time Event Controllers | 60 | 3900 | FE, BE | UI event creation dispatch (e.g. Town Hall, Tornado Alert triggers)
| Layer 2: API Gateway & Security - APIM (BFF) & Entra B2C Auth Setup | 120 | 7800 | SA, BE | Token auth, Rate Limiting, Zero Trust architecture
| Layer 3: Compute - Transaction & Ledger Service (Core Banking Engine) | 210 | 13650 | BE | SQL persistence, Idempotency tracking
| Layer 3: Compute - Configuration & Town Map Service | 60 | 3900 | BE | Cosmos DB configuration bindings
| Layer 3: Compute - Basic Gamification Progression Service (No AI) | 60 | 3900 | BE | Standard progression APIs (Integrates with Admin Controller triggers)
| Layer 3: Compute - Analytics & Reporting Service | 80 | 5200 | BE, Data | Read-replica historical reports
| Layer 4: Async Event-Bus - Azure Service Bus Provisioning | 50 | 3250 | DevOps, BE | Event choreography messaging infrastructure
| Layer 5: Observability & Validation - QA, Load Tests, App Insights, Store Deployment | 270 | 17550 | QA, Sec, PM | E2E bugs, Distributed Tracing integration
| Sub-Total | 1680 | 109200
| PM (10%) | 168 | 10920
| Year 1 Support (Hyper-Care & Maintenance) | 1200 | 78000 | 1 FTE | Post-launch monitoring
| Total | 3048 | 198120
| Man Months | 11.6 |  |  | Based on 160h/month
Notes
These estimates represent the core MVP ONLY (Option B), strictly categorised by the essential Azure Microservices.
Mobile App, Admin Staff Portals (Controls, Tornado Events, User Mgmt), and SDLC processes are distinctly itemized for transparency.