## Sheet1
Phase | Feature (Module Area) | Hours | Cost | Team | Comments
Phase 1: Core MVP | Layer 1: Edge & UI - UX Design, Student PWA, Staff Admin SPA, Teacher Dashboard UI | 750 | 48750 | Designer, FE | React/React Native interfaces
| Layer 1: Edge & UI - Azure Front Door & Static Web Apps Setup | 40 | 2600 | DevOps | Edge caching infrastructure
| Layer 2: API Gateway & Security - APIM (BFF) & Entra B2C Identity Integration | 120 | 7800 | SA, BE | Token auth, Rate Limiting, Zero Trust
| Layer 3: Compute - Transaction & Ledger Service (Core Banking) | 210 | 13650 | BE | SQL persistence, Idempotency tracking
| Layer 3: Compute - Configuration & Town Map Service | 60 | 3900 | BE | Cosmos DB bindings
| Layer 3: Compute - Basic Gamification Logic (No AI) | 60 | 3900 | BE | Standard progression API
| Layer 3: Compute - Analytics & Reporting Service | 80 | 5200 | BE, Data | Read-replica reports
| Layer 4: Async Event-Bus - Azure Service Bus Provisioning & Topics | 50 | 3250 | DevOps, BE | Event choreography setup
| Layer 5: Observability & Validation - E2E Testing, App Insights, WCAG, Store Deployment | 310 | 20150 | QA, Sec, PM | Tracing, Load Testing, Circuit breakers
| Sub-Total | 1680 | 109200
| PM (10%) | 168 | 10920
| Year 1 Support (Hyper-Care & Maintenance) | 1200 | 78000 | 1 FTE | Post-launch monitoring
| Total | 3048 | 198120
| Man Months | 11.6 |  |  | Based on 160h/month
Notes
These estimates represent the core MVP ONLY (Option B), strictly categorised by the essential Azure Microservices.
All optional AI, hardware SDKs, intricate math, and dedicated environments (Phase 2 items) have been stripped to keep delivery highly streamlined.