## Sheet1
Phase | Feature | Hours | Cost | Team | Comments
Phase 1: Core MVP | System Architecture & Setup: 3 environments, Core Cloud Setup | 120 | 7800 | SA, DevOps | Infrastructure Design + CI/CD
| UX/UI Conceptualization & Prototyping: Core flows, WCAG 2.2 AA | 130 | 8450 | Designer, FE | No Generative AI visuals
| Backend Core Simulation & Financial Engine: Basic Banking, Ledgers, APIs | 210 | 13650 | BE | Entra B2C Auth, Unlimited Inventory Assumption
| CMS & Multi-Tenant Administration: React UI for Staff, Static Template downloads | 280 | 18200 | FE, BE
| Mobile Apps & Web Dashboards: Student React Native SPA, Teacher Dashboard | 470 | 30550 | FE, BE | Tablet Camera QR usage
| Gamification Core & Basic Reporting: Simple Progression API, Historical BI Views | 170 | 11050 | BE, Data
| Testing, Delivery, & App Store: E2E, Bug Fixes, Accessibility Auditing | 300 | 19500 | QA, Sec, PM
| Sub-Total | 1680 | 109200
| PM (10%) | 168 | 10920
| Year 1 Support (Hyper-Care & Maintenance) | 1200 | 78000 | 1 FTE | Post-launch monitoring
| Total | 3048 | 198120
| Man Months | 11.6 |  |  | Based on 160h/month
Notes
These optimized estimates deliver Phase 1 ONLY (The Core MVP).
Phase 2 features (Luxury AI, External Hardware, True Offline Sync, Dynamic PDFs) are completely deferred.
Creates a highly stable, affordable launch platform strictly focused on the core simulation.