JA BizTown 3.0 Redevelopment

Comprehensive Project Estimation & Analysis Report

Date: April 08, 2026    |    Rate: $85/hr (blended)    |    Budget Cap: $1,000,000

# 1. Executive Summary

This report presents the comprehensive project estimation and analysis for the redevelopment of the JA BizTown 3.0 simulation platform. The analysis is grounded in a full review of the JA BizTown RFP, all 143 vendor Question & Answer responses, and a proposed Azure-native microservices architecture designed to support 10,000–15,000 concurrent users across 60–70 simultaneous simulations nationwide.

Two distinct estimate models are presented in this document:

| Estimate Model | Total Cost | Dev Hours | Scope | Budget Target | Key Distinction |
| --- | --- | --- | --- | --- | --- |
| Revised Estimate | $748,340 | 6,310 dev hrs | Phase 1 + Phase 2 | $850K | Full scope within $750K budget target |
| Realistic Estimate | $995,775 | 8,120 dev hrs | Phase 1 + Phase 2 + 10% Contingency | $1,000,000 | Most accurate full-scope with explicit risk buffer |

Both estimates are designed within JA's confirmed $1,000,000 budget cap (Q25 response) at a blended rate of $85 per hour. Each estimate includes Year 1 and Year 2 post-launch support, PM/delivery management overhead, and all explicit Q&A-driven scope requirements identified during the 143-question vendor clarification process.

# 2. Key Q&A Findings That Drive Estimates

A thorough review of all 143 vendor Q&A responses yielded the following critical findings that directly impact scope, architecture, and effort estimates:

| Q&A Ref | Finding | Impact | Details |
| --- | --- | --- | --- |
| Q7, Q15, Q133 | Offline Local-First Required | Phase 1 Mandatory | System must support local-first operation with sync. No full reversion to paper. |
| Q16 | Business Scenarios = Grant Req. | Phase 1 Mandatory | Character education (ethical dilemmas, XP consequences) must be included for grant funding. |
| Q13, Q135 | Canva Marketing Tool | Phase 1 Mandatory | Template-based tool; step-by-step mission; image library; publish to town display. |
| Q14, Q131 | CFO Screen Sharing | Phase 1 Mandatory | Real-time screen mirror to 14-20 business sessions simultaneously; no audio. |
| Q17, Q45 | DJ Radio Dashboard | Phase 1 Mandatory | Built-in DJ UI; playlist + mic; adapts to diverse A/V systems across 98 Areas. |
| Q137 | Physical Debit Card Readers | Phase 1 Mandatory | 3-digit account number swiped into POS. Current production model — must continue. |
| Q110 | Data Anonymization (30-day) | Phase 1 Mandatory | COPPA compliance: student data anonymized 30 days post-simulation. |
| Q68 | Spanish Localization | Phase 1 Mandatory | Vendor expected to provide all translated content. |
| Q77, Q78 | Pilot On-Site Support | Phase 1 Required | Vendor must be on-site for select pilot sessions; instant availability for rest. |
| Q25, Q26 | Budget Cap: $1M | Hard Constraint | Total project cost must not exceed $1,000,000 for initial release. |
| Q125, Q126 | 10-15K Concurrent Users | Hard Constraint | 60-70 simultaneous simulations; 50-100 TPS during peak shopping periods. |
| Q143 | Full State Recovery (DR) | Hard Constraint | Simulations MUST resume from exact prior state. Restarting is not acceptable. |
| Q136 | AI Features (Slogan + Speech) | Phase 2 Optional | Flexible for pilot; can be introduced post-launch if timeline is tight. |
| Q19, Q138 | NFC Tap-to-Pay | Phase 2 Optional | Nice-to-have; graceful QR code degradation required. Cross-platform iOS + Android. |
| Q134 | Paper Fallback | Not Required | Not required if offline digital mode is functional. |
| Q23 | Shared Devices | Removed | One device per student. Shared device model has been eliminated. |
| Q71 | Student Accounts | Simplified | Session-based per device; no individual student accounts or PII collected. |
| Q57 | Azure Deployment | Collaborative | JA provides Azure environment; vendor owns pipeline config and permissions. |

# 3. Azure-Native Microservices Architecture

The proposed architecture is built on a 5-layer Azure-native microservices model. The system is designed around event-driven choreography, idempotent transaction processing, and zero-trust security principles to ensure the simulation survives massive concurrency spikes and unstable facility WiFi environments.

| Layer | Name | Azure Technologies | Key Responsibilities |
| --- | --- | --- | --- |
| Layer 1 | Edge & UI Delivery | Azure Front Door, CDN, Static Web Apps | Student PWA, Teacher Dashboard, Admin CMS, DJ Radio, Marketing Tool |
| Layer 2 | API Gateway & Security | Azure APIM (BFF), Entra B2C, Key Vault | Auth, JWT tokens, RBAC, rate-limiting, payload transformation |
| Layer 3 | Compute (Microservices) | AKS (Docker containers), Azure SQL, Cosmos DB, Redis Cache | Banking, Offline Sync, Gamification, Reporting, Voting, Scenarios |
| Layer 4 | Async Event-Bus | Azure Service Bus | Decouples banking from gamification; guarantees at-least-once delivery |
| Layer 5 | Observability & Resilience | Azure Monitor, App Insights, Polly Circuit Breaker | Correlation ID tracing, distributed telemetry, graceful degradation |

## 3.1 Idempotency & Transaction Safety

Because facility WiFi is unreliable, student tablets may inadvertently retry payment requests multiple times. The Transaction & Ledger Service accepts a unique Idempotency-Key (UUID) on every mutation request. On a duplicate retry, the service checks Azure Cache for Redis, recognizes the key, and returns the same successful response without double-charging the student's ledger. This pattern is enforced across all financial microservices.

## 3.2 Offline Local-First Architecture

Per Q7/Q133, the system must support local-first operation with eventual sync. Student devices queue all transactions locally when offline. Upon reconnect, the queue syncs sequentially with a conflict reconciliation engine on the server side — ensuring every student's balance and business ledger reaches consistency without data loss. No on-premise server is required; this is a cloud-hybrid resilience pattern.

## 3.3 Scale Requirements

Per Q125/Q126, the system must support 10,000–15,000 concurrent users across 60–70 simultaneous simulations. Peak throughput reaches 50–100 transactions per second during shopping periods. AKS autoscaling, read-replica SQL, and Azure Service Bus topic partitioning are the primary mechanisms used to achieve this scale without degradation.

# 4. Revised Estimate — $750K Budget Target

The Revised Estimate targets a total project cost of approximately $750,000 at $85/hr blended. It includes all Phase 1 (Core MVP) features and all Phase 2 (Optional) features, with the hours calibrated precisely to land within the target budget. All Q&A-mandatory items are included in Phase 1.

| Category | Hours | Cost |
| --- | --- | --- |
| Dev (Phase 1 + Phase 2) | 6,310 hrs | $536,350 |
| PM / Delivery Mgmt (11%) | 694 hrs | $58,990 |
| Year 1 Support (1 FTE) | 1,200 hrs | $102,000 |
| Year 2 Support (0.5 FTE) | 600 hrs | $51,000 |
| TOTAL | 8,804 hrs | $748,340 |

## 4.1 Phase 1 — Core MVP Highlights

| Area | Hours | Description |
| --- | --- | --- |
| Foundation | 340 hrs | Requirements, Architecture (10-15K scale), CI/CD, Docker Dev Setup, Data Anonymization |
| UX / UI | 1,870 hrs | Full design system, PWA app, 6 student role UIs, CMS inheritance, Canva tool, CFO sharing, Radio, Voting |
| API Gateway | 130 hrs | APIM BFF, Entra B2C session auth |
| Backend Compute | 1,480 hrs | Banking (50-100 TPS), Offline Sync, Config, Business Scenarios, Debit Card, XP, Reporting, Audit, DR |
| Event Bus | 70 hrs | Azure Service Bus with dead-letter handling |
| Testing & Security | 1,080 hrs | Automated tests, WCAG, Pen testing, Load testing, Cross-device, UAT |
| Delivery | 310 hrs | App Store, User guides, Spanish localization, Pilot support, Post-pilot sprint |

## 4.2 Phase 2 — Optional Features

| Feature | Hours | Notes |
| --- | --- | --- |
| AI Slogan Generation | 120 hrs | Scaffolded Azure OpenAI; 3-strike guardrail; age-appropriate constrained outputs |
| AI Speech-to-Text | 80 hrs | CEO speech transcription and in-simulation display (not AI speech writing) |
| NFC Tap-to-Pay | 160 hrs | iOS + Android NFC with graceful QR fallback across device types |
| Advanced Gamification | 140 hrs | Inventory depletion; supply chain math beyond unlimited stock assumption |
| 4th QA Environment | 40 hrs | Isolated regression + load test cluster separate from Dev/Staging/Prod |

# 5. Realistic Estimate — Full Scope with 10% Contingency

The Realistic Estimate represents the most accurate full-scope projection, incorporating all Phase 1 and Phase 2 features, with more thorough and precise hourly allocations for high-complexity items. A 10% contingency buffer is explicitly included as a named line item — not hidden — to account for scope creep, integration surprises, and unknowns that invariably emerge during a project of this complexity.

| Category | Hours | Cost |
| --- | --- | --- |
| Dev (Phase 1 + Phase 2) | 8,120 hrs | $690,200 |
| Contingency Buffer (10%) | 812 hrs | $69,020 |
| PM / Delivery Mgmt (11%) | 983 hrs | $83,555 |
| Year 1 Support (1 FTE) | 1,200 hrs | $102,000 |
| Year 2 Support (0.5 FTE) | 600 hrs | $51,000 |
| GRAND TOTAL | 11,715 hrs | $995,775 |

The Realistic Estimate comes in at $995,775 — just under the JA-confirmed $1,000,000 budget cap. The additional hours vs the Revised Estimate reflect more thorough allocations for genuinely high-risk items including the offline sync engine, real-time screen sharing, full DR state recovery, comprehensive QA cycles, and pilot on-site support logistics.

## 5.1 Key Differences vs Revised Estimate

| Feature | Revised Hrs | Realistic Hrs | Rationale |
| --- | --- | --- | --- |
| Offline Sync Engine | 220 hrs | 260 hrs | More complex reconciliation logic; edge case handling |
| Transaction & Ledger | 320 hrs | 360 hrs | More thorough idempotency + audit coverage |
| Performance Engineering | 200 hrs | 220 hrs | Additional simulation load scenarios |
| Post-Pilot Sprint | 280 hrs | 280 hrs | Same — already conservative |
| Automated Test Suite | 280 hrs | 280 hrs | Same |
| DR & State Recovery | 120 hrs | 130 hrs | Full walkthrough validation included |
| Voting Service (Backend) | 70 hrs | 80 hrs | Separate microservice for civic ballot processing |
| Payroll Engine | 70 hrs | 70 hrs | Explicitly itemized (was bundled in banking) |
| Team Building / Onboarding | 50 hrs | 60 hrs | Guided first-time walkthroughs per Q42 |
| Post-Launch Hypercare | 60 hrs | 60 hrs | First-week instant-availability support Q78 |
| 10% Contingency | N/A | 812 hrs | Explicit risk buffer — not in Revised |

# 6. Side-by-Side Comparison

| Metric | Revised Estimate | Realistic Estimate |
| --- | --- | --- |
| Total Dev Hours | 6,310 | 8,120 |
| Contingency | Not included | 812 hrs (10%) |
| PM Overhead | 694 hrs (11%) | 983 hrs (11%) |
| Year 1 Support | 1,200 hrs | 1,200 hrs |
| Year 2 Support | 600 hrs | 600 hrs |
| Total Hours | 8,804 hrs | 11,715 hrs |
| Total Cost (@ $85/hr) | $748,340 | $995,775 |
| Budget Headroom | $251,660 | $4,225 |
| Phase 1 Coverage | Full | Full |
| Phase 2 Coverage | Full | Full |
| Contingency Buffer | None | 10% explicit |
| Voting Module | Included | Separately itemized |
| Payroll Engine | Bundled | Separately itemized |
| Hypercare (Week 1) | Included | Separately itemized |
| Risk Level | Medium | Low (buffered) |

## 6.1 Recommendation

For a project of this complexity — 100+ JA Area facilities, 10-15K concurrent users, real-time financial transactions, hardware integrations, and a hard January 2027 pilot deadline — the Realistic Estimate ($995,775) is the recommended baseline for client presentation. The explicit 10% contingency protects both the vendor and JA from mid-project scope discussions, and the more thorough hourly allocations reflect what a quality delivery actually requires.

The Revised Estimate ($748,340) remains a valuable option if JA wishes to preserve maximum budget headroom for future feature phases, hardware procurement, or Year 3 onwards support. Both models fall within the confirmed $1M budget cap.

# 7. Technology Stack Summary

| Technology | Layer | Role in JA BizTown |
| --- | --- | --- |
| React / React Native | UI / Frontend | Cross-platform PWA for student tablets and admin SPAs on laptops |
| Azure Front Door & CDN | Edge & Delivery | Global edge entry point; WAF; DDoS protection; static asset caching |
| Azure Static Web Apps | Edge & Delivery | Serverless hosting for all frontends; built-in CI/CD; free SSL |
| Azure API Management (APIM) | API Gateway | BFF pattern; rate-limiting; tablet vs desktop payload transforms |
| Microsoft Entra B2C | Security/Identity | Session-based auth; JWT tokens; RBAC for all user types |
| Azure Key Vault | Security | All secrets managed via Managed Identities; zero-secret-in-code |
| Docker | Infrastructure | Containerizes all microservices for identical local/cloud builds |
| Azure Kubernetes Service (AKS) | Infrastructure | Orchestrates and autoscales containers; zero-downtime deployments |
| Azure SQL Database | Data Persistence | ACID-compliant for all financial transactions and student ledgers |
| Azure Cosmos DB | Data Persistence | Flexible JSON documents for BizTown config and facility layouts |
| Azure Cache for Redis | Data Persistence | Idempotency key tracking; prevents duplicate payment processing |
| Azure Web PubSub / SignalR | Real-Time Comms | WebSocket push for screen sharing, town alerts, DJ announcements |
| Azure Service Bus | Async Messaging | Event-driven choreography; decouples banking from reporting/XP |
| Azure Monitor & App Insights | Observability | Correlation ID tracing across all services for root-cause analysis |
| Polly (Circuit Breaker) | Resilience | Retry + circuit break policies preventing cascading failures |
| Microsoft Power BI | Analytics | BI layer for aggregate simulation data; export from CMS |
| Azure OpenAI | AI (Phase 2) | Managed LLM for slogan generation; speech-to-text transcription |

# 8. Project Timeline & Key Milestones

| Period | Milestone | Description |
| --- | --- | --- |
| May 2026 | Project Kickoff | In-person kickoff; vendor volunteers at live JA BizTown simulation (Q10/Q27) |
| May–Aug 2026 | Discovery & Architecture | UX research, wireframes, architecture finalization, Azure environment setup |
| Jun–Oct 2026 | Design & Core Development | Visual design system; all Phase 1 microservices; CMS build-out |
| Sep–Nov 2026 | Integration & Testing | Cross-service integration; load testing; WCAG audit; security pen testing |
| Nov 2026 | Area Training & Site Prep | JA Area staff training; MDM distribution; pre-pilot preparation (Q96) |
| Jan–Mar 2027 | Pilot Phase (10-15 JA Areas) | Full-feature pilot; vendor on-site at select Areas; instant availability for rest |
| Apr 2027 | Post-Pilot Sprint | Remediation of pilot feedback; defect triage; enhancement evaluation |
| Jun 2027 | Initial Release | Full national release; all JA Areas can opt in to new platform (Q98) |
| Jun 2027+ | Year 1 Hyper-Care | 1 FTE support; 100% uptime M-F 8AM-7PM ET; incident escalation model |
| Jun 2028+ | Year 2 Maintenance | Annual upgrade cycle; infrastructure refresh; minor enhancements |

# 9. Key Risks & Mitigations

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Offline Sync Conflicts | High | High | Mature conflict resolution strategy in architecture phase; idempotency everywhere |
| WiFi Instability at Facilities | High | Medium | Local-first queue; degraded-mode digital operation; no paper fallback needed |
| Hardware Variability (NFC, Card Readers) | Medium | Low | NFC is Phase 2; card reader SDK designed for graceful fallback to manual entry |
| Scope Creep from Discovery | High | Low | 10% contingency explicitly budgeted; JA governance process for scope changes (Q2) |
| Timeline Tightness (Jan 2027 pilot) | High | Medium | Aggressive but feasible with dedicated team; post-pilot sprint buffers final release |
| Legacy A/V System Diversity | Medium | Low | DJ dashboard designed for wide adaptability (Bluetooth to built-in speakers) |
| Device OS Fragmentation | Medium | Low | PWA single codebase; cross-device testing matrix in QA budget |
| Third-Party Audit Delays (WCAG) | Low | Low | JA has existing auditor relationship; vendor coordinates remediation |
| AI Guardrail Failures | Low | Low | Phase 2; 3-strike retry limit; output filtering; no open-ended AI interaction |

————————————————————————————————————————

This document is confidential and proprietary. All estimates are based on the JA BizTown 3.0 RFP and Q&A responses dated March 2026. Rate: $85/hr blended. Generated: April 08, 2026.